## Suivi S08
SD-ITM-LNK-010-00 | Origin | Document | ID | Requirement Title | Screen | To be reworked due to V1 evolutions
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-PRC-000-00 | Updateable fields according to items status | S08 et plus
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DTL-000-00 | Menu from Item Detail screen | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DTL-010-00 | Item tab screen layout | S08 | TBRW
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DTL-020-00 | Job Description text area | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DTL-030-00 | Corrective Action text area | S08 | TBRW
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DTL-040-00 | Corrective Action tab screen layout | S08
ItemCorAction | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DTL-050-00 | Corrective Action to be done text area | S08
ItemCorAction | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DTL-060-00 | Answer text area | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DTL-070-00 | Responsible | S08 | Replaced by SPEC-UC03-004
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DTL-080-00 | Remark | S08
Responsible | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RES-000-00 | Introduction | S08
Responsible | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RES-010-00 | General Description | S08
Responsible | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RES-030-00 | Responsible Field | S08
Responsible | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RES-040-00 | List Of Values | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-000-00 | Item creation access | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-010-00 | Item creation: one by one | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-020-00 | General Description | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-030-00 | Production flag initialization | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-040-00 | Production flag modification | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-060-00 | Items displayed to customers | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-070-00 | User interface | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-080-00 | Permissions | S08 | A préciser
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-120-00 | A/P/S or Cabin Items creation | S08 | Maquette
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-130-00 | Permissions | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-230-00 | Item update | S08 | TBRW
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-240-00 | Navigation rules from the Item Detail form | S08
LogbookClosure | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CRT-250-00 | Automatic creation of last item | S08
ItemClosure | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CLS-000-00 | Item Closure :General Description | S08
ItemClosure | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-CLS-010-00 | HIL item Closure | S08
ReportItem | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RPT-000-00 | Report item to a new one | S08
ReportItem | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RPT-010-00 | Report item to a CAP form | S08
ReportItem | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RPT-020-00 | Item's link | S08 | TBRW (un item avec des fils peut quand même être reporté)
ReportItem | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RPT-030-00 | General Description | S08
ReportItem | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RPT-040-00 | Technical Report of an Item | S08 | TBRW (exigence ne devrait plus exister)
ItemLink | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-LNK-000-00 | Link Creation - General rules | S08 | TBRW
ItemLink | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-LNK-010-00 | Link an item to a Father/Son screen | S08
ItemLink | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-LNK-020-00 | At the link creation | S08
ItemLink | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-LNK-030-00 | Link Father/Son deletion | S08
ItemLink | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-LNK-040-00 | Navigation between linked items | S08 | TBRW V1.0
ItemStamp | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-STP-000-00 | Final Stamp | S08
ItemStamp | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-STP-010-00 | Final Stamp Process | S08 | TBRW Zone closure
Item Refusal | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-RFS-000-00 | Item Refusal | S08 | TBRW Subject status
ItemClosure | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-ACC-000-00 | Crew Acceptance | S08 | TBRW
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DSP-000-00 | Display all items - General rules | For Information / To test for regression
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-DSP-010-00 | Display all Items access | For Information / To test for regression
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-ATA-000-00 | ATA and SUB-ATA origin | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-ATA-010-00 | ATA format | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-ATA-020-00 | ATA :Use of the List Of Values | S08
ItemDetail | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-ATA-030-00 | ATA :Without use of the List Of Values | S08
ItemStamp | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-ZLR-000-00 | Zone Closure domain | S08
ItemStamp | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-ZLR-010-00 | Zone Closure Actions | S08
ItemStamp | Spec Legacy | TLBV1_SD_Item_V1.0.doc | SD-ITM-ZLR-020-00 | Zone Closure results | S08
AttachDoc | Spec Legacy | TLBV1_SD_AttachedFiles_V1.0.doc | SD-ATF-SCR-020-00 | Attached Files tab content | S08 | TBRW
AttachDoc | Spec Legacy | TLBV1_SD_AttachedFiles_V1.0.doc | SD-ATF-SCR-030-00 | Attached Files business rule | S08 | TBRW
AttachDoc | Spec Legacy | TLBV1_SD_AttachedFiles_V1.0.doc | SD-ATF-SCR-040-00 | Attached files - item report actions from Item Detail screen | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-000-00 | Main Responsible: User Access | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-010-00 | User Interface | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-020-00 | Recipients | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-030-00 | Current user e-Mail address | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-040-00 | Additional Text | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-050-00 | Subtask Responsible :User Access | S08 | TBRW Maquette + 4 responsible
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-060-00 | User Interface | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-120-00 | Permissions | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-130-00 | Operating conditions | S08 | TBRW Database access to SMTP server
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-140-00 | E-Mail Received | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-150-00 | Fax Received | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL160-00 | E-Mail Error Status Received | S08
SendMail | Spec Legacy | TLBV1_SD_FaxMail_V1.0.doc | SD-FAX-MAL-170-00 | Fax Error Status Received | S08
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-GEN-000-00 | General Description | S08
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-FUL-000-00 | Job Card Fuel | S87
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-FUL-010-00 | Generated Text | S87
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-WEI-000-00 | Job Card Weighing - User Interface | S82
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-WEI-010-00 | A/C Weighing area details | S82
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-WEI-020-00 | Aside Measurements area details | S82
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-WEI-030-00 | A/C Configuration area details | S82
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-WEI-040-00 | Generated Text | S82
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-000-00 | User Interface | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-010-00 | General Description | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-020-00 | FIN field | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-030-00 | P/N field | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-040-00 | Equipment Change Type | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-050-00 | Comment field | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-060-00 | Copy button | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-070-00 | Swap button | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-080-00 | Electronic Signatures | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-090-00 | Document Type | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-100-00 | Generated Text | S81
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ECH-110-00 | Job Card Equipment Changes for A400M | S98
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-CSI-000-00 | User Interface | S80
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-CSI-010-00 | Administration | S80
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-CSI-020-00 | Applicability Date' on Job Cards Croquis and Special Instruction | S80
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-CSI-030-00 | Generated Text | S80
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-PST-000-00 | Job Cards Post Flight and Post Engine Run - Description | S84/S86
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-PST-010-00 | Job Cards Post Flight and Post Engine Run - User Interface | S84/S86
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-PST-020-00 | Saving Action | S84/S86
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-PRE-000-00 | Job Cards Pre Flight and Pre Engine Run - Description | S83/S85
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-PRE-010-00 | Job Cards Pre Flight and Pre Engine Run - User Interface | S83/S85
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-PRE-020-00 | Saving Action | S83/S85
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-EXW-000-00 | Job Card External Work | S90
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-EXW-010-00 | Generated Text | S90
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-FTL-000-00 | Flight Test Loading Plan | S88
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-FTL-010-00 | Generated Text | S88
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-SOL-000-00 | Starter Oil Level | S89
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-000-00 | Add a configuration | For Information / To test for regression
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-010-00 | Delete a configuration | For Information / To test for regression
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-020-00 | Fuel Job Card : General Information | S87
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-030-00 | Fuel job card configuration access | For Information / To test for regression
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-040-00 | Fuel job card configuration screen | For Information / To test for regression
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-050-00 | Configuration area details | For Information / To test for regression
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-060-00 | Configuration details area details | For Information / To test for regression
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-070-00 | Weighing job card configuration access | For Information / To test for regression
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-080-00 | Weighing job card configuration screen | For Information / To test for regression
JobCards | Spec Legacy | TLBV1_SD_JobCards_V1.0.doc | SD-JCD-ADM-090-00 | Job Card Administration | S08
PreFormattedTexts | Spec Legacy | TLBV1_SD_PreFormattedTexts_V1.0.doc | SD-PFT-CSL-000-00 | Pre-formatted texts access | S08
PreFormattedTexts | Spec Legacy | TLBV1_SD_PreFormattedTexts_V1.0.doc | SD-PFT-CSL-010-00 | Pre-formatted texts window | S08
PreFormattedTexts | Spec Legacy | TLBV1_SD_PreFormattedTexts_V1.0.doc | SD-PFT-CRT-020-00 | Pre-formatted Texts Groups Administration / Users Profiles Affectation form | For Information / To test for regression
PreFormattedTexts | Spec Legacy | TLBV1_SD_PreFormattedTexts_V1.0.doc | SD-PFT-CRT-030-00 | Pre-formatted Texts" Tab | For Information / To test for regression
PreFormattedTexts | Spec Legacy | TLBV1_SD_PreFormattedTexts_V1.0.doc | SD-PFT-CRT-040-00 | User profiles | For Information / To test for regression
PreFormattedTexts | Spec Legacy | TLBV1_SD_PreFormattedTexts_V1.0.doc | SD-PFT-CRT-050-00 | Classification | For Information / To test for regression
PreFormattedTexts | Spec Legacy | TLBV1_SD_PreFormattedTexts_V1.0.doc | SD-PFT-CRT-060-00 | Pre-formatted Texts Administration form | For Information / To test for regression
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-SQC-000-00 | User Interface Sequencing | For Information / To test for regression
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-FTA-000-00 | General Description | For Information / To test for regression
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-FTA-010-00 | Global Refresh | For Information / To test for regression
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-FTA-020-00 | Cyclic Daily Refresh | For Information / To test for regression
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-FTA-030-00 | Refresh by User Request | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-APL-000-00 | Installed SI : Operating conditions | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-APL-010-00 | Closed SI : Operating conditions | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-APL-020-00 | Aborted SI :Operating conditions | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-APL-030-00 | In progress SIs | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-APL-040-00 | SIs Information | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-000-00 | Create SI Item Access | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-010-00 | SI Item creation in server mode | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-020-00 | SI Filter | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-030-00 | SI List | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-040-00 | Selected SI List (SI to apply) | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-050-00 | Item Creation | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-060-00 | Forms creation | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-070-00 | Manual SI creation | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-080-00 | Manual SI creation | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-090-00 | SI Application Rollback | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-CRT-100-00 | Permissions | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ADD-000-00 | Add SI Application Access | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ADD-010-00 | Add SI Applications : Operating conditions | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ADD-020-00 | Add SI Application in Server mode | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ADD-030-00 | Add SI Application in local mode | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ADD-040-00 | Item Modification | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ADD-050-00 | Permissions | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ABR-000-00 | Aborted SI Application Access | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ABR-010-00 | Aborted SI Application Access | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ABR-020-00 | Aborted SI Application Access | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ABR-030-00 | Item Modification | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-ABR-040-00 | Item Modification | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-MNG-000-00 | Operating conditions | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-MNG-010-00 | SI preview and attached documents | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-MNG-020-00 | SI Item Crew acceptance without Final Stamp | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-MNG-030-00 | SI Item Crew acceptance with Final Stamp | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-MNG-040-00 | SI Item Refusal | S93
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-MNG-050-00 | Change TLB milestone | For Information / To test for regression
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-MNG-060-00 | BRD-TAC-010 | For Information / To test for regression
SI Items | Spec Legacy | TLBV1_SD_SI_Management_V1.0.doc | SD-SIM-FRM-000-00 | Operating conditions | S93
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-GDS-000-00 | Concerned Logbook | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-GDS-010-00 | Types of MPD Tasks | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-GDS-020-00 | Applicability of MPD Tasks | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DFS-000-00 | Pilot Phase | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DFS-010-00 | Interface | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DFS-020-00 | Identification of the MPD Tasks | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DFS-030-00 | Format of period and visibility of the task in the csv file | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DFS-040-00 | Registration of csv file name | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DFS-050-00 | MPD Items generation | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DFS-060-00 | Algorithm of the job | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DSC-070-00 | MPD task status - How to compute them | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DSC-080-00 | Time sequence for MPD | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DSC-090-00 | Content of the MPD Item | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DSC-100-00 | MPD Tasks in Item List screen | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DSC-110-00 | MPD Tasks in Item Detail screen | S08
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DSC-120-00 | Report of a MPD Item | S08
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DSC-130-00 | Refuse of a MPD Item | S51
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DSC-140-00 | Logbook locking | For Information / To test for regression
MPD Items | Spec Legacy | TLBV1_SD_MPDTasks_V1.0.doc | SD-MPD-DSC-150-00 | MPD Tasks List | For Information / To test for regression
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-000-00 | Paper Copy mode generalities | For Information / To test for regression
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-010-00 | Logbook Creation | For Information / To test for regression
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-020-00 | Technical Logbook List | For Information / To test for regression
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-030-00 | Enter/Update text in items | S08
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-040-00 | Item Renumbering | For Information / To test for regression
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-050-00 | Item Deletion | For Information / To test for regression
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-060-00 | Item Status | S08
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-070-00 | Closure of items | S08
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-080-00 | HIL items | S08
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-090-00 | Reopen items | S08
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-100-00 | Other status | S08
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-110-00 | Item Input | S08
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-120-00 | Reports of items/Links | S08
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-130-00 | Check on Paper mode | For Information / To test for regression
PaperMode | Spec Legacy | TLBV1_SD_PaperCopy_V1.0.doc | SD-PPR-MNG-140-00 | Job cards on Paper mode | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-001 | Extension of allowed file format for attached files | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-002 | View attached files | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-003 | Print attached files | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-004 | Define attached file by Drag & Drop | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-005 | Upgrade size limit of attached file | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-008 | File attachment extended to Nomad Workstation | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-009 | File attachment upload from NWS
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-HMI-001 | Attached File area | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-HMI-002 | Attached File Job Description Drop Area | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-HMI-003 | Attached File Corrective Action Drop Area | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-HMI-004 | List of attached files | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-HMI-005 | Attached File access | S08
AttachDoc | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-HMI-006 | Attached File Print | S08
HistoryList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC02-001 | New Logbook access to subject History | S08
HistoryList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC02-002 | Content of subject Status History | S08
HistoryList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC02-003 | Access to Item content from Status History | S08
HistoryList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC02-004 | No Status History limitation for Xfer subjects | S08
HistoryList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC02-HMI-001 | Access History from Subject Detail | S08
HistoryList | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC02-HMI-002_01 | History List content | S08
HistoryList | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC02-HMI-003_01 | History List Theme | S08
HistoryList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC02-HMI-004 | Access Subject Detail from History | S08
HistoryList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC02-HMI-005 | History List Window (To be reviewed) | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04-001 | Multi-links between subjects | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04-002 | Multi-links allowed during report | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04-003 | Persistence of links when reported from check to check | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04-004 | No link to grand-father | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04-005 | No link from grand-son | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04-006 | Subject Link Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04-007 | Type of Link in Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04-008 | Access to Linked Subjects from the Subject Link Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04-009 | Removal of links from the Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC04-010 | Creation of manual link from SI Item | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-001 | Selection of sons subjects | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-002 | Link deletion button removed | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-003 | Link Creation button removed | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-004 | Go to Father / Go to Son buttons removed | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-005 | Access to Subject Link Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-006 | Subject Link Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-007 | Subject representation in Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-008 | Subject Job Description in Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-009 | Link representation in Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-010 | Link Orientation representation in Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-011 | Link Selection representation in Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-012 | Select Link in Link Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-013 | Unselect Link in Link Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-014 | Select of Several Links in Link Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-015 | Removal of Selected Links in Link Logical Diagram | S08
ItemLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- HMI-016 | Link Creation in Logical Diagram | S08
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-001 | Migration of legacy logbook one by one
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-002 | Migration of the whole set of legacy closed logbook at once
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-002A | Legacy Items Identification
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-002B | Legacy Logbook Identification
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-003 | Closed Legacy logbooks in new TLB application
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-004 | FTEST logbooks in new TLB application
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-005 | Subject generation during migration
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-005A | Subject Status generation during migration
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-006 | Subject Corrective Action generation during migration
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-007 | Filtering of TLB creation in the new TLB system | S02
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC06-008 | Filtering of TLB creation in the legacy application (LEGACY) | S02
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC06-009_01 | Consultation of migrated logbooks in the legacy application (LEGACY)
Migration | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC06-010 | Range of ID_LOGB in New TLB | S02
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC08-001_01 | Creation of Hyper-Links from free input | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-001A | Hyper-Links removal/modification | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-002 | Hyper-Links Types | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-003 | Creation of Hyper-Links to TSM from PFR | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-004 | Creation of Hyper-Links to AMM from MPD Task | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-005 | Creation of Hyper-Links to AMM from Job Card Equipment Change | S81
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-006 | Creation of Hyper-Links to SI Corporate from SI Items | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-007 | Definition of Hyper-Links target | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-IHM-001 | Hyper-Links Rendering in read-only fields | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-IHM-002 | Hyper-Links Rendering in field editor | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-IHM-003 | Existing Airn@v button behavior | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-IHM-004 | Existing TSM button behavior | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-IHM-005 | Existing SI Access button behavior | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-IHM-006 | Duplication of Hyper-Links by Copy/Paste | S08
HyperLinks | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC08-IHM-007 | Pasting in target reference input field | S08
ItemSubCat | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC09-001 | Sub-category of a subtask | S08
ItemSubCat | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC09-002 | Final Stamp of pure cosmetic subject | S08
ItemSubCat | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC09-004 | Sub-category in Corrective Action | S08
ItemSubcat | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC09-005 | Sub-category in Reports | S08
SearchSubCat | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC09-006_01 | Search Cosmetic and/or Technical Subjects | S07
ItemSubCat | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC09-IHM-001_01 | Sub-Category rendering at the sub-task level | S08
SearchSubCat | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC09-IHM-002 | Search Cosmetic Subject | S07
SubjReOpen | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC10-001 | Subject Re-opening | S08
SubjReOpen | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC10-002 | Reason for subject re-opening | S08
SubjReOpen | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC10-003 | Management of re-opened subject properties | S08
SubjReOpen | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC10-IHM-001 | Re-Open Subject from Admin menu | S08
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-032 | Reference to subject/items in CAP Forms | S64
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-032A | Reference to subject/items in MPD Tasks Administration | SM1
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-032B | Reference to subject/items in PFR Detail | S74
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-032C | Reference to subject/items in SI Item Creation , Installed SI and add SI application | S94
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-032D | Subject Number display customization in CAP Forms, MPD, PFR and SI forms | S64/S74/S94/SM1
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-010 | Subject Identification in CAP Forms | S64
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-010A | Subject Identification in MPD Tasks Administration | SM1
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-010B | Subject Identification in PFR Detail | S74
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-010C | Subject Identification in SI Item Creation and Installed SI | S94
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-011 | Subject Identification in CAP Forms | S64
Interfaces | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-INT-001 | Maintain legacy Item numbering for interfaces projects
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-016 | Print Dialog Subject Identification
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-001 | Subject/Items Logbook Report List
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-002 | Subject/Items Logbook Report presentation
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-003 | New Logbook Report List Check presentation
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-004 | Daily Status for Customer Report Status translation | R01
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-005 | Delivery Logbook Customer Print Corrective Action | R02
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-006 | Outstanding Work Listing Corrective Action | R03
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-007 | Flight Logbook Customer Print Corrective Action | R04
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-008 | TLB Print Corrective Action | R05
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-009 | Items List Print Input Dialog
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-010 | Items List Print Corrective Action
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-011 | Print Front Page
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-012 | Item/Subject Header for one item per page report
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-013 | Item Print Report Corrective Action
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-013A | Sub-Task Presentation
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-014 | Sub-Task Presentation with multi-answers
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-015 | TLB Consultation Corrective Action
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-015A | Technical Logbook Paper Backup Front Page
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-016 | SI List Presentation
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-017 | MPD Task List Presentation
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-REP-018 | AIR Follow-Up Print List
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC02-REP-001 | History Report for selected Item | New Report
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC02-REP-002 | Multi- Items Subject Report List | R14
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC04- REP-001 | Manual Links List Print Report | R14
Report | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC05-REP-001 | Attached File Print in Airbus Technical Logbook Report
TLBConsult | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC01-033_01 | Technical Logbooks Consultation per logbook mode
TLBConsult | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-034 | Technical Logbooks Consultation mixed List
TLBConsult | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-035 | Technical Logbooks Consultation Subject Numbers
TLBConsult | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-036 | Technical Logbooks Consultation legacy subjects
TLBList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-042 | TLB List: add logbook mode criterion
TLBList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-043 | TLB List total per status
TLBConsult | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-012 | Technical logbook Consultation Search Criteria (To be reviewed) | S20
TLBConsult | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-013 | Technical logbook Consultation List Subject Number
TLBList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-014 | TLB List Prod check-box
Welcome | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-015 | Welcome screen Prod check
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-001 | Subject identification | S08
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-002 | Subject Identification Numbering | S08
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-003 | Customer Acceptance Subject Identification | S08
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-004 | Xfer Subjects
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-005 | Format of Subject Number | S08
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-006 | Format of Item Reference | S08
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC01-007_01 | Item Reference Display customization
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC01-008_01 | Subject Number Display customization
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC01-009_01 | Item or Subject Oriented customization
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-011 | Subject Status | S08
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-037 | New Logbook Subject Number/Item reference display in Message
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-038 | Legacy Logbook Item Reference display in Message
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-039 | New logbook and Customer change
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-040 | Coexistence of legacy items and new TLB items in FTEST logbook
ItemGeneral | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-041 | FTEST logbook cross-migration subjects
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-GEN-001 | Actions Confirmation | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-GEN-002 | Message Identification | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-GEN-003 | Message Identification | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-GEN-004 | Screen Access Authorizations | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-GEN-005 | Actions Authorizations | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-HMI-001 | Standard Keyboard shortcuts | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-024 | Subject Identification in Subject Detail | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-025 | No more Sum-up of related links | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-026 | Subject corrective action | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-028 | Customer Acceptance Subject Detail for Xfer Item | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-029 | Customer Acceptance Subject Corrective Action for Xfer Item | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-030 | Corrective Action Size and Technical Report | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-007 | New Logbook Subject Detail Item Identification
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-008 | New Logbook Subject Detail Check Identification
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-009 | No more Link Browsing from the Subject Detail
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-014 | Subject Detail main form | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-HMI-015 | Focus on Item Properties and Corrective Actions | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-016 | Subject Detail Form and Subject History | S08
ItemDetail | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-017 | Auto- resizing of Subject Detail form | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-001 | Subject detail: Corrective action to be Done mandatory | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-002 | Subject Detail: self-explanatory sub-task | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-003 | Subject Detail: Unlimited sub-tasks | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-004 | Subject Detail: Multi-responsible per subtask | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-005 | Subject Detail: Unlimited answers | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-006 | Subject Detail: Default behavior for Insertion of Corrective Actions to be done | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-007 | Subject Detail: Insertion of subtasks anywhere | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-008 | Subject Detail: Default behavior for Insertion of answer related to subtask | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-009_01 | Subject Detail: Default behavior for Insertion of self-explanatory subtask (to be reviewed)
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-010 | Subject Detail: Insertion of answers anywhere | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-011 | Subject Detail: Insertion of self-explanatory answers anywhere | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-012 | Subject Detail: Management of reported items | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-014 | Partial Stamp/ Done on subtask | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-015 | Report of subtasks in new Item | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-016 | Reported Item and Outstanding work | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-017 | Subject Detail: Check on first subtask associated to Job-card | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-018_01 | Subtask Acknowledge | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-019 | Subtask number shall be displayed (To be reviewed) | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-020 | Subject Detail: Identify found text from criteria | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-021 | Remove Job Card Croquis | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-001 | Automatically collapse stamped sub-tasks | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-HMI-002 | Manual expand/collapse sub-task | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-002A | Refresh the current subtask list | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-HMI-003 | Differentiate partially stamped subtasks within outstanding work | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-HMI-004_01 | Identify done or partially stamped sub-tasks from previous check | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-HMI-005_01 | Add answer to a collapsed subtask | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-006_01 | Filter Subtasks | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-007 | Presentation of subtasks | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC03-HMI-008_01 | Void answer waiting | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-009 | Order of subtasks | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-011 | Subject Detail: Subtasks display order | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-012 | Subject Detail: Answers display order | S08
ItemCorAction | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC03-HMI-013 | Subject Detail: Access to the last updated subtask | S08
Nomad | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC01-044_01 | Archive content
AltScreens | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC01-045 | AIR Follow-up automatic check of historic Items | S56
Item Detail | Spec NewTLB | TLB_V1.0_SD_V1.0.1Draft1.doc | SPEC-UC01-46 | Remove Report attached files confirmation | S07/S08
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-012 | Multi-items subjects in Subject/Item List
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-012A | Xfer subject displayed as Created in Customer Acceptance | S07/S08
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-013 | Manual Link Network in Subject/Item List
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-014 | Subject List Criteria applicability
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-015 | Item List Criteria applicability (To be reviewed) | S07
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-016 | Subject List Criteria Status
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-017 | Item List Criteria Status
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-018 | From/to Subject Number Criteria on Subject List
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-019 | Display Subjects in Customer Acceptance | S07
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-021 | Subject Number /Customer Acceptance Subject Number in Subject List
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-022 | Subject List Sort Order
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-023 | Subject Status in Subject/Item List | S08
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-027 | Subject/Item corrective action display | S07
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-001 | New Logbook Subject List Presentation
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-002 | New Logbook Subject List Criteria Presentation
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-003 | Subject Number criteria
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-004 | New Logbook Subject List Ending Check Criteria init
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-005 | New Logbook Subject List Ending Date Criteria init
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC01-HMI-006 | New Logbook Subject List Status Colors
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC11-001 | Link Information in Subject List
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC11-002 | Multi-Items Subjects in Subject List
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC11-IHM-001 | Subjects List Enhancements
ItemList | Spec NewTLB | TLB_V1.0_SD_V1.0.doc | SPEC-UC11-IHM-002 | Auto resizing of Subjects/Item List
Note on C214: Req Modified SD 1.0.1
Note on C215: Req Modified SD 1.0.1
Note on C227: Req added SD 1.0.1 Implemented in ATX version
Note on C255: Req Modified SD 1.0.1
Note on C256: Req Modified SD 1.0.1
Note on C257: Req Modified SD 1.0.1
Note on C276: Req Modified SD 1.0.1
Note on C319: Req Modified SD 1.0.1
Note on C335: Req Modified SD 1.0.1
Note on C360: Req Modified SD 1.0.1
Note on C371: Req Modified SD 1.0.1
Note on C373: Become a duplicate of SPEC-UC03-007, shall be removed.
Note on C379: Req completely rewritten SD 1.0.1
Note on E379: Previous title : Subtask Acknowledge for self-explanatory subtask
Note on C382: Req added SD 1.0.1
Note on E382: JobCard Croquis is S80, but it is called from S08 Corrective Action
Note on D384: add mockup screen to this req in SD 1.0.1
Note on D386: Precision added to this req according to mockup
Note on C387: Req Modified SD 1.0.1
Note on C388: Req Modified SD 1.0.1
Note on E388: Previous title : Add answer to collapsed corrective action
Note on E391: Previous title : Void corrective action/void answer
Note on G391: added 03/02/2015 -Marc Monge
Note on C396: Req Modified SD V1.0.1
Note on C397: Req Added SD V1.0.1
Note on C398: Req Added SD V1.0.1
Note on F398: Report HIL implemented in S07 (ATX) and in S08 (WPF). To be fixed in S07 and to be implemented with automatic report of attached files in WPF